## Sheet1
MUSIC RECOMMENDATION CAPSTONE PROJECT (TEAM MAVERICKS) | [6 empty] | PROJECT TIMELINE & WORK LOAD DISTRIBUTION
Task ID | Task | Assigned to | Tentative Start Date | Tentative End Date | Milestone? | Status | October | [17 empty] | November | [29 empty] | December
[7 empty] | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Web App Development Stack Initialization | Rishabh Malhotra | 2022-10-14 | 2022-10-15 | No | In Progress | [62 empty] | Work by Both | bar: October 14 to October 15
2 | CI/CD Pipeline Setup for Web App | Rishabh Malhotra | 2022-10-15 | 2022-10-18 | No | Not Started | [62 empty] | Work by Rishabh Malhotra | bar: October 15 to October 18
3 | User Registration Page | Jatin Arora | 2022-10-18 | 2022-10-20 | No | Not Started | [62 empty] | Work by Jatin Arora | bar: October 18 to October 20
4 | User Login Page | Jatin Arora | 2022-10-20 | 2022-10-21 | No | Not Started | bar: October 20 to October 21
5 | Preference Selection Page | Jatin Arora | 2022-10-21 | 2022-10-23 | No | Not Started | bar: October 21 to October 23
6 | Recommendation View Page | Jatin Arora | 2022-10-23 | 2022-10-27 | No | Not Started | bar: October 23 to October 27
7 | Baseline Model Development | Both | 2022-10-16 | 2022-10-25 | No | Not Started | bar: October 16 to October 25
7.1 | Data Preprocessing and EDA | Both | 2022-10-16 | 2022-10-18 | No | Not Started | bar: October 16 to October 18
7.2 | Model Development | Rishabh Malhotra | 2022-10-18 | 2022-10-23 | No | Not Started | bar: October 18 to October 23
7.3 | Model Evaluation | Rishabh Malhotra | 2022-10-23 | 2022-10-24 | No | Not Started | bar: October 23 to October 24
7.4 | Model Deployment | Rishabh Malhotra | 2022-10-24 | 2022-10-25 | No | Not Started | bar: October 24 to October 25
8 | Web App and Baseline Model Integration | Both | 2022-10-25 | 2022-10-29 | No | Not Started | bar: October 25 to October 29
9 | Web App (Product) QA | Both | 2022-10-29 | 2022-11-02 | No | Not Started | bar: October 29 to November 2
10 | Minimum Viable Product - Web App with Baseline Model | Both | 2022-11-03 | 2022-11-03 | Yes
11 | Search and Filter Functions | Jatin Arora | 2022-11-04 | 2022-11-07 | No | Not Started | bar: November 4 to November 7
12 | User Feedback Mechanism | Jatin Arora | 2022-11-07 | 2022-11-11 | No | Not Started | bar: November 7 to November 11
13 | Content based Filtering Approach (with song lyrics and metadata) Model Development | Both | 2022-11-05 | 2022-11-18 | No | Not Started | bar: November 5 to November 18
13.1 | Data Preprocessing and EDA | Both | 2022-11-05 | 2022-11-10 | No | Not Started | bar: November 5 to November 10
13.2 | Model Development | Rishabh Malhotra | 2022-11-10 | 2022-11-14 | No | Not Started | bar: November 10 to November 14
13.3 | Model Evaluation and Baseline Model Comparision | Rishabh Malhotra | 2022-11-14 | 2022-11-16 | No | Not Started | bar: November 14 to November 16
13.4 | Model Deployment | Rishabh Malhotra | 2022-11-16 | 2022-11-18 | No | Not Started | bar: November 16 to November 18
14 | Web App and Content Based Model Integration | Both | 2022-11-18 | 2022-11-21 | No | Not Started | bar: November 18 to November 21
15 | Web App (Product) QA | Both | 2022-11-21 | 2022-11-23 | No | Not Started | bar: November 21 to November 23
16 | Minimum Marketable Product - Enhanced Web App with Content Based Filtering Approach model | Both | 2022-11-24 | 2022-11-24 | Yes
17 | Song Player Integration | Jatin Arora | 2022-11-25 | 2022-11-28 | No | Not Started | bar: November 25 to November 28
18 | API Development for Third Party Access | Rishabh Malhotra | 2022-11-28 | 2022-12-01 | No | Not Started | bar: November 28 to December 1
19 | Hybrid Approach Model (Content based filltering + Collaborative Filtering) Development | Both | 2022-11-25 | 2022-12-03 | No | Not Started | bar: November 25 to December 3
19.1 | Data Preprocessing and EDA | Both | 2022-11-25 | 2022-11-27 | No | Not Started | bar: November 25 to November 27
19.2 | Model Development | Rishabh Malhotra | 2022-11-27 | 2022-12-01 | No | Not Started | bar: November 27 to December 1
19.3 | Model Evaluation and Previous Model Comparisions | Rishabh Malhotra | 2022-12-01 | 2022-12-02 | No | Not Started | bar: December 1 to December 2
19.4 | Model Deployment | Rishabh Malhotra | 2022-12-02 | 2022-12-03 | No | Not Started | bar: December 2 to December 3
20 | Web App and Hybrid Approach Model Integration | Both | 2022-12-03 | 2022-12-05 | No | Not Started | bar: December 3 to December 5
20 | Web App (Product) QA | Both | 2022-12-05 | 2022-12-07 | No | Not Started | bar: December 5 to December 7
21 | Product Ready to Launch - Web App with all features powered by Hybrid Approach Recommendation Model | Both | 2022-12-08 | 2022-12-08 | Yes
22 | Project Presentation | Both | 2022-12-15 | 2022-12-15 | Yes